## Tasks
ID | Fred tracker ID | Workstream | Journey | Task | Owner | Org | Priority | Due | Status | Depends on | Notes / source
A1 | TECH-01 | Planning & documentation | All | Fill updated journey doc columns (policy/technical questions, readiness gaps, Discussion) for J1–J4.1 | RM | Nawi | Critical path | 2026-10-20 | In progress |  | Before Wed 21 Oct sync; cell text drafted
A2 | TECH-03 | Planning & documentation | All | Fix dated vignette timeline (birth date, 6-month visit, travel date) so test data and schedule rules agree | RM | Nawi | Critical path | 2026-10-20 | Not started | B1 | Coordinate with RR test data
A3 | TECH-09 | Planning & documentation | All | Full requirements / technical specification document (production-level requirements even where implementation is mock) | RM | Nawi | Critical path | 2026-10-23 | Not started | A1 | Carl: document at production level
A4 | TECH-09 | Planning & documentation | All | IG scaffold on WHO repo: BPMN process diagrams, user stories, terminology, test data, links to DVC / VHL / PCF specs | RM / CL | Nawi/WHO | Critical path | 2026-11-06 | Not started | A3 | Agreed 16 Oct; also shown as best-practice workflow documentation
A5 | JOINT-01 | Planning & documentation | All | Weekly sync (next: Wed 21 Oct 13:00 Geneva); add AeHIN and Mark to invite | CL / FH | WHO/Google | Critical path | 2026-10-21 | In progress
A6 | TECH-03 | Planning & documentation | J1–J3 | Request real vaccine lists from two countries (via AeHIN) so the code-set discrepancy is concrete | CL | WHO | Nice to have | TBC | Not started |  | Carl suggestion 16 Oct
B1 | TECH-03 | Issuance & test data | J1 | Single-vaccine DVC / IPS example from existing test-bed data; confirm it matches a newborn first-dose story | RR | WHO | Critical path | 2026-10-19 | In progress |  | Hajj / Rexel examples; content embedded in QR, no portal lookup
B2 | TECH-03 | Issuance & test data | J1 | Document QR-generation steps | RR | WHO | Critical path | 2026-10-19 | Not started
B3 | TECH-03 | Issuance & test data | J1 | Requirements doc from Hajj / Rexel scenarios (basis for verification API requirements) | RR | WHO | Critical path | 2026-10-19 | Not started |  | Reviewed Monday per Carl
B4 | TECH-03 | Issuance & test data | J1 | Generation tool for test DVCs if existing data does not fit the story | CL | WHO | Critical path | 2026-10-23 | Not started | B1
B5 | TECH-03 | Issuance & test data | J1 | Locate and review Roxel wiki documentation | CL | WHO | Nice to have | 2026-10-23 | Not started
B6 | TECH-02 | Issuance & test data | J1 | Pre-printed QR cards + optional pre-recorded issuance video | CL / RR | WHO | Critical path | 2026-10-24 | Not started | B1 | Issuance is simulated, not live
B7 | TECH-03 | Issuance & test data | J3 | Provision DEV trust-list keys / PKI material for demo devices | CL | WHO | Critical path | 2026-10-22 | Not started |  | https://smart.who.int/trust/endpoints.html
C1 | TECH-04 | Verification library | J3, J4.1 | Pull verifiers repo (last Rexel update) and confirm it runs | RR | WHO | Critical path | 2026-10-19 | Not started |  | gdhcn-validator
C2 | TECH-04 | Verification library | J3, J4.1 | Review API requirements doc; identify gaps for the library | CL / JCT / RM | WHO/Nawi | Critical path | 2026-10-20 | Not started | B3
C3 | TECH-04 | Verification library | J3, J4.1 | Transcode Python validator REST API to Kotlin | JCT | WHO | Critical path | 2026-10-22 | Not started | C2
C4 | TECH-04 | Verification library | J3, J4.1 | Deliver Kotlin multiplatform QR/HCERT extraction + DVC and VHL-manifest verification library to Nawi for testing | CL | WHO | Critical path | 2026-10-23 | Not started | C3 | 'mid next week' per Carl
C5 | TECH-05 | Verification library | J2, J3, J4.1 | QR reader component working cross-platform (Android; web on tablet) | Nawi eng | Nawi | Critical path | 2026-10-27 | Not started |  | Fred: priority
C6 | TECH-06 | Verification library | J3, J4.1 | Integrate verification library into OHS Player (J3 DVC verify; J4.1 manifest verify) with cached keys for offline | Nawi eng | Nawi | Critical path | 2026-11-04 | Not started | C4, C5
D1 | TECH-09 | Player configurations | J1–J3 | Terminology: ValueSets country-a-vaccines / country-b-vaccines, deliberately unmapped, one shared vaccine coded differently | Nawi eng | Nawi | Critical path | 2026-10-30 | Not started | A2
D2 | TECH-05 | Player configurations | J2 | Community config: household roster, newborn registration, QR decode (no verify), Immunization as unverified (primarySource=false, reportOrigin), referral ServiceRequest to seeded facility | Nawi eng | Nawi | Critical path | 2026-10-28 | Not started | C5, D1
D3 | TECH-06 | Player configurations | J3 | EHR config (web on tablet / Android): scan, verify, import with Provenance, PlanDefinition/FHIRPath schedule vs Country B rules, reminder Task/Appointment | Nawi eng | Nawi | Critical path | 2026-11-04 | Not started | C6, D1
D4 | TECH-07 | Player configurations | J4.0 | Family config: member profiles (Group/RelatedPerson), pull records, one VHL QR per traveller with passcode | Nawi eng | Nawi | Critical path | 2026-11-10 | Not started | E1 | Three VHLs / IPS / QRs: mother, father, baby
D5 | TECH-07 | Player configurations | J4.1 | Viewer config: scan VHL QR, passcode, fetch manifest, verify, display | Nawi eng | Nawi | Critical path | 2026-11-10 | Not started | C6, E1
D6 | TECH-03 | Player configurations | All | Seed data and fixed dates for demo devices | Nawi eng | Nawi | Critical path | 2026-10-28 | Not started | A2, B1
D7 | TECH-10 | Player configurations | J3, J4.1 | AuditEvent at Info Gateway for verification and VHL fetches | Nawi eng | Nawi | Critical path | 2026-11-12 | Not started | D3, D5
D8 | TECH-10 | Player configurations | J4.0 | Consent-to-share captured at VHL generation (Consent / AuditEvent; IHE PCF as reference) | Nawi eng | Nawi | Nice to have | TBC | Not started | D4 | Nice-to-have / commentary per Fred
D9 | TECH-07 | Player configurations | J4.0 | SMS / WhatsApp delivery of records or links | Nawi eng | Nawi | Nice to have | TBC | Not started | D4 | Deferred
E1 | TECH-08 | VHL issuer / host | J4.0, J4.1 | Mock VHL issuer: FHIR server exposing VHL endpoints with the three IPS, signed; hosted on Nawi OHS servers | Nawi eng / JCT | Nawi/WHO | Critical path | 2026-11-06 | Not started | B1 | Small mock, not Docker-heavy; requirements still production-level
E2 | TECH-08 | VHL issuer / host | J4.0 | Evaluate OpenFn approach to fetch from FHIR server and package IPS / VHL payloads | RM | Nawi | Nice to have | 2026-10-30 | Not started
E3 | TECH-08 | VHL issuer / host | J4.0, J4.1 | ITB VHL issuer prototype (reference / test environment) | CL / WHO | WHO | Critical path | 2026-10-30 | Not started |  | Targeted week of 27 Oct
E4 | TECH-08 | VHL issuer / host | J4.1 | Fallback: pre-packaged VHL QR codes handed to Nawi | CL / RR | WHO | Critical path | TBC | Not started |  | Used if E1/E3 slip
E5 | TECH-07 | VHL issuer / host | J4.0 | Sync with Jing on prior SHL / portable-record work | RM | Nawi | Critical path | 2026-10-21 | Not started
E6 | TECH-08 | VHL issuer / host | J4.0 | Hunt Roxel team VHL demos and open-source tools | CL | WHO | Nice to have | 2026-10-23 | Not started
E7 | TECH-10 | VHL issuer / host | J4.0 | Review IHE Privacy Consent on FHIR (PCF) for consent breakout content | RM | Nawi | Nice to have | 2026-10-23 | Not started
F1 | TECH-11 | Workshop content | J5 | Nawi content / code-lab plan (partially assembled kits, steps 3, 7, 11; curated final assembly) | RM / FH | Nawi/Google | Critical path | 2026-11-14 | Not started |  | Initial plan already shared
F2 | TECH-11 | Workshop content | J5 | Legacy-system mapping as short tech talks + demos (not a breakout) | FH | Google | Critical path | TBC | Not started
F3 | POL-06 | Workshop content | All | Align partner and country demonstration slots (CSIRO, OpenFn, TH, ID, MY, LA, KH) | GM / DW / AM | WHO | Critical path | 2026-11-12 | Not started |  | Section 4 of doc
F4 | POL-05 | Workshop content | All | Policy-track discussion points: code-set governance, consent (PCF), audit / GDPR-style access, DVC vs ICVP | CL / Mark | WHO | Critical path | 2026-11-10 | Not started | A4
F5 | TECH-12 | Workshop content | J5 | Day 2 interoperability practicum stations and test scripts (source-to-FHIR, use and update, test and exchange; optional ITB test harness) | RM / CL | Nawi/WHO | Critical path | 2026-11-18 | Not started | F1
F6 | JOINT-04 | Workshop content | All | Day 2 connected end-to-end demo run-of-show (community referral to clinic verification to cross-border travel) | RM / CL / FH | Nawi/WHO/Google | Critical path | 2026-11-22 | Not started | D3, D4, D5, E1
F7 | TECH-13 | Workshop content | All | Full end-to-end technical rehearsal with offline fallbacks and failure recovery | RM / FH / CL | Nawi/Google/WHO | Critical path | 2026-11-25 | Not started | F6
Note on I1: Dates stated on the 14 and 16 Oct calls are used where given; other dates are suggested targets to confirm with the team. 'TBC' = not yet scheduled.

## Summary
Workshop date (Mon–Tue, confirm) | 2026-11-30
By owner
Owner | Total | Not started | In progress | Blocked | Done | Critical path
RM | 12 | 11 | 1 | 0 | 0 | 10
RR | 6 | 5 | 1 | 0 | 0 | 6
CL | 16 | 15 | 1 | 0 | 0 | 13
JCT | 3 | 3 | 0 | 0 | 0 | 3
FH | 5 | 4 | 1 | 0 | 0 | 5
Nawi eng | 12 | 12 | 0 | 0 | 0 | 10
WHO (other) | 1 | 1 | 0 | 0 | 0 | 1
Note: shared tasks (e.g. 'CL / RR') count once under each named owner.
By workstream
Workstream | Total | Done | Open | Critical path open
Planning & documentation | 6 | 0 | 6 | 5
Issuance & test data | 7 | 0 | 7 | 6
Verification library | 6 | 0 | 6 | 6
Player configurations | 9 | 0 | 9 | 7
VHL issuer / host | 7 | 0 | 7 | 4
Workshop content | 7 | 0 | 7 | 7
Due this week / overdue
Open tasks due on or before | 2026-10-23 | 17
Legend
Yellow cells are for you to edit (owner, priority, due, status on Tasks; workshop date and cut-off here).
Owners: RM Roy Munge · RR Ritika Rawlani · CL Carl Leitner · JCT Jose Costa Teixeira · FH Fred Hersch · GM/DW/AM Garrett Mehl / Diana Wijayanti / Alvin Marcelo · Nawi eng = Nawi engineering team.
Due dates: items stated on the 14 and 16 Oct calls are as given; the rest are aligned to the parent task dates in Fred Hersch's master tracker (Fred tracker ID column). Keep that tracker as the master; this sheet is the technical sub-task breakdown.
Summary formulas recalculate as the Tasks sheet changes; add new rows anywhere on Tasks.
Note on A1: 30 Nov to 1 Dec 2026, Bangkok, per Fred Hersch project plan (github.com/fredhersch/pre-gdhf-workshop).

## Milestones
Date | Milestone | Owner | Status
2026-10-19 | Single-vaccine DVC/IPS example + QR steps + API requirements doc | RR | In progress
2026-10-20 | Journey doc columns filled; timeline fixed; API requirements reviewed | RM / CL / JCT | In progress
2026-10-21 | Weekly sync — VHL approach confirmed, verification library requirements reviewed | All | Not started
2026-10-23 | Kotlin verification library delivered to Nawi (TECH-04) | CL / JCT | Not started
2026-10-28 | J2 community config reads QR offline and refers (TECH-05) | Nawi | Not started
2026-11-04 | J3 clinic config verifies signatures and calculates schedule (TECH-06) | Nawi | Not started
2026-11-06 | Mock VHL issuer live; IG published on WHO repo (TECH-08, TECH-09) | Nawi / WHO | Not started
2026-11-10 | J4.0 and J4.1 family configs resolve three VHLs (TECH-07) | Nawi | Not started
2026-11-14 | Day 1 code labs packaged (TECH-11) | FH / RM | Not started
2026-11-25 | Full end-to-end rehearsal (TECH-13) | All | Not started
2026-11-30 | Pre-GDHF workshop, Bangkok, 30 Nov to 1 Dec | All | Not started
Milestone dates follow Fred Hersch's master plan (TECH/JOINT IDs); sub-task dates on the Tasks sheet are set to land before their parent.