## Workshop Overview
THAILAND DIGITAL HEALTH WORKSHOP • END-TO-END REGIONAL USER JOURNEYS (J1 - J5)
Master Architecture, Plenary Anchors, Parallel Breakout Tracks (Technical & Policy), and Governance Integration Framework
TOTAL SESSIONS |  | PROGRAMMED HOURS |  | JOURNEYS COVERED |  | TRACK DELIVERABLES
18 Sessions |  | 16.0 Hours |  | 5 of 5 (100%) |  | 16 Deliverables
9 Day 1 • 9 Day 2 Sessions |  | 2 Full Days (09:00 - 17:00) |  | J1, J2, J3, J4 (J4.0/J4.1), J5 |  | 10 Technical • 6 Policy Products
1. END-TO-END JOURNEY ARCHITECTURE & PARALLEL BREAKOUT TRACK MATRIX
Journey ID | Journey Name & Focus | Operational Real-World Scenario | Plenary Anchor Session | Technical Track Objectives | Policy & Governance Track Objectives | Target Core Deliverable | Lead Standards
Journey J0 | FHIR, Interoperability, terminology level settings
Journey J1 | Cross-Border Birth & Initial Vaccination | Mother delivers abroad in Asia; receives routine newborn vaccines (Hep B, Polio); clinic issues signed paper Digital Vaccine Certificate (DVC) with QR code. | Day 1 (09:30 - 09:45): E2E Walkthrough of Cross-Border Birth & Initial DVC Issuance | FHIR Patient & Immunization modeling, QR payload encoding (SHC / DDCC), PKI trust list validation, schema mapping. | Legal recognition of foreign DVCs, birth dose schedule alignment, CRVS birth notification abroad without bilateral treaties. | Validated DVC QR payload format & cross-border PKI trust model. | WHO DDCC, FHIR R4, SMART Cards
Journey J2 | Return Home, CHW Discovery & Referral | Family returns home; Community Health Worker (CHW) discovers unregistered infant during home visit; logs offline QR metadata; creates clinic referral. | Day 1 (10:45 - 11:00): Household CHW Discovery, Offline QR Reading & Clinical Referral | Offline-first Android CHW app (OHS Player), QR reading at edge without signature verification, ServiceRequest FHIR referral workflow. | CHW legal scope of practice, handling unverified foreign records prior to clinic triage, cross-border vaccine code mapping. | Offline CHW data sync protocol & ServiceRequest referral specification. | OHS Player (Android), FHIR ServiceRequest
Journey J3 | Clinic Verification & Schedule Generation | Family attends clinic referral with paper QR; provider cryptographically validates foreign DVC, imports immunization into domestic EHR, and evaluates schedule rules. | Day 1 (13:00 - 13:15): Clinic Cryptographic Verification & Clinical Schedule Generation | Kotlin Multiplatform verification library, FHIR Provenance resource tagging, PlanDefinition/FHIRPath schedule evaluation against national rules. | Trust-list key governance (national trusted anchors), adjudicating unmapped foreign vaccine codes, patient consent for automated reminders. | Clinical verification algorithm & domestic PlanDefinition ruleset. | Kotlin Multiplatform, FHIR Provenance, PlanDefinition
Journey J4 | Outbound Family Travel ("One Family, One Phone") | National portal issues portable health records (IPS & DVCs) to shared family smartphone with passcode-protected Verifiable Health Link (VHL) QR code for point-of-care fetch. | Day 2 (09:00 - 09:45): Outbound Travel, Multi-Profile Mobile VHL & Point-of-Care Clinic Fetch | Multi-profile device management in OHS Player, VHL Issuer mock service, AuditEvent logging, passcode decryption & verification via shared library. | Minor/dependent consent sharing, VHL link expiration & retention limits, cross-border legal basis for data access, audit trail governance. | Multi-record VHL configuration & audit trail governance policy. | Verifiable Health Links (VHL), IPS, AuditEvent
Journey J5 | Projectathon Practicum & Joint Demonstration | Multi-country teams execute end-to-end exchange testing across sandbox stations (FHIR validation, REST APIs, WHO-ITB test suites), concluding with plenary demonstration. | Day 2 (11:00 - 17:00): Projectathon Exchange Testing, Rehearsal & Joint Demonstration | Hands-on FHIR mapping, StructureMap execution, FHIR Validator CLI runs, REST API transactions, WHO-ITB ICVP test suites. | Country implementation readiness assessments, institutional interoperability governance, regional trust framework roadmap. | Validated country interoperability test matrix & joint policy declaration. | HL7 FHIR R4, REST APIs, WHO-ITB Gazelle
Synthesis Note: Each journey weaves Plenary alignment with specialized Technical (implementation) and Policy (governance) breakout tracks.
2. REGIONAL PARTICIPATION & COUNTRY ARCHITECTURE MATRIX
Member State | National Workshop Role | Core Digital Health Systems & Registries | Key Journey Anchors | Technical Implementation Focus | Policy & Governance Priority | Delegation Lead / Agency
Thailand (Host) | Host Nation & Regional Verification Anchor | Mor Phrom Platform, MOPH Health Data Center (HDC), National Digital Health Platform (NDHP) | J1, J3, J4, J5 | Kotlin Multiplatform verification library deployment, FHIR Terminology Server, Host Test Node | Regional trust-list governance, cross-border consent framework, bilateral data accords | Ministry of Public Health (MOPH)
Indonesia | Cross-Border Verification & Mobile Node | SatuSehat Platform, SATUSEHAT Mobile, PeduliLindungi Immunization Registry | J1, J2, J4, J5 | SatuSehat FHIR API adapter, VHL Issuer mock endpoint, multi-profile mobile credentials | Bilateral trust registry recognition, minor dependent consent & data retention policy | Ministry of Health (Kemenkes) / DTO
Malaysia | Interoperability Node & Schedule Engine | MyVAS (Vaccine Administration System), MySejahtera, MOH Health Information Exchange | J1, J3, J4, J5 | PlanDefinition immunization schedule engine, ConceptMap vaccine code translation, FHIR Provenance | Clinical adjudication policy for foreign non-equivalent vaccine codes, key rotation protocols | Ministry of Health Malaysia (MOH)
Lao PDR | Cross-Border Community Discovery & Intake | DHIS2 Immunization Tracker, National CRVS Registry, District Health Information System | J1, J2, J3, J5 | Offline-first Android CHW application (OHS Player), edge QR metadata extraction, ServiceRequest sync | CHW legal scope of practice for foreign record logging, cross-border borderland health accords | Ministry of Health Lao PDR (DPC / DHP)
Cambodia | Community Discovery & Referral Node | CamLIS, National Immunization Program (NIP) Database, Community Health Information System | J2, J3, J5 | Offline QR reader metadata extraction, clinic EMR FHIR ingestion, local terminology mapping | CRVS birth notification integration, verification protocol for unverified maternal records | Ministry of Health Cambodia (CDC / DIMS)
Regional Synthesis: All 5 member states participate across technical hands-on testing stations and policy governance consensus tracks.

## Day 1 Agenda
THAILAND WORKSHOP • DAY 1 AGENDA: FOUNDATIONS, DATA MAPPING & EARLY JOURNEYS (J1 - J3)
Schedule: Day 1 (09:00 - 17:00) • Venue: Bangkok Grand Ballroom & Breakout Wings A & B • Focus: Cross-Border Newborns, Community Health Worker Discovery & Clinical Verification
Time Block | Duration | Journey Ref | Session Format | Plenary Anchor & Joint Scope | Comments | Technical Breakout (Room A) | Technical Guiding Questions | Policy & Governance Breakout (Room B) | Policy Guiding Questions | Session Output / Deliverable | Execution Status
08:30 - 09:30 | 30 min | Framing | Plenary Session | Workshop Opening & E2E User Journey Framing (J1 - J5) |  | All Participants in Grand Ballroom | How do end-to-end user journeys connect community, clinic, and national health architectures across ASEAN? | All Participants in Grand Ballroom | What are the shared governance principles and legal prerequisites for regional interoperability? | Workshop Roadmap & Cross-Track Collaboration Charter | Scheduled
09:30 - 10:30 | 60 min | Journey J1 | Plenary & Breakouts | J1 Walkthrough: Cross-Border Birth & Initial DVC Issuance (15m Plenary intro) |  | Tech Breakout (45m): FHIR Patient & Immunization Modeling, QR Payload Mapping (SHC / DDCC) & PKI Trust Setup | QR code generation/printing vs smartphone; mapping source vax data to FHIR/DVC standards; PKI trust list governance for dev/test; code system translation. | Policy Breakout (45m): Legal Recognition of Foreign DVCs, Schedule Alignment & CRVS Birth Notification | Birth dose schedule differences across borders; applicable vaccine code systems; CRVS & birth notification abroad; legal recognition of routine DVC from Country A in Country B without bilateral agreement. | J1 FHIR Mapping Model & Cross-Border DVC Acceptance Guideline | Scheduled
10:30 - 10:45 | 15 min | Intermission | Health Break | Morning Networking & Refreshments Break |  | Grand Foyer Refreshments & Technical Setup Check | N/A - Technical Preparation | Grand Foyer Refreshments & Policy Networking | N/A - Informal Dialogue | Informal Networking & System Readiness Check | Scheduled
10:45 - 12:00 | 75 min | Journey J2 | Plenary & Breakouts | J2 Walkthrough: Household CHW Discovery & Offline Clinic Referral (15m Plenary intro) |  | Tech Breakout (60m): Offline Android CHW App (OHS Player), QR Reader Component & ServiceRequest FHIR Referral | Offline-first Android CHW app; OHS Player QR reader component (payload decoding without signature verification at edge); facility registry for referrals via ServiceRequest. | Policy Breakout (60m): CHW Scope of Practice, Unverified Foreign Record Handling & Code Mapping | Cross-border vaccine code mapping; linkage to CRVS; policy for CHWs acting/referring on unverified foreign records before clinical verification. | Offline CHW Referral Specification & CHW Cross-Border Field Protocol | Scheduled
12:00 - 13:00 | 60 min | Intermission | Meal Break | Networking Luncheon & Multi-Country Team Sync |  | Dining Pavilion & Country Team Pods | N/A - Team Coordination | Dining Pavilion & Country Team Pods | N/A - Team Coordination | Cross-Country Alignment & Bilateral Sync | Scheduled
13:00 - 14:30 | 90 min | Journey J3 | Plenary & Breakouts | J3 Walkthrough: Cryptographic Trust, DVC Verification & Clinic EMR Import (15m Plenary intro) |  | Tech Breakout (75m): Kotlin Verification Library, FHIR Provenance & PlanDefinition Schedule Generation | OHS Player web/tablet EMR; verification via shared Kotlin multiplatform library; Provenance resource tagging; PlanDefinition/FHIRPath immunization schedule evaluation against domestic rules. | Policy Breakout (75m): Trust-List Key Governance, Code Adjudication & Patient Consent Policies | Adjudicating foreign vaccine codes with no equivalence map; trust-list governance (which authority keys clinic trusts); consent for appointment reminders. | Verified DVC Ingestion Pipeline & National Trust-List Governance Matrix | Scheduled
14:30 - 14:45 | 15 min | Intermission | Health Break | Afternoon Refreshments & Workstream Transition |  | Grand Foyer Refreshments | N/A - Technical Setup | Grand Foyer Refreshments | N/A - Policy Exchange | Informal Networking | Scheduled
14:45 - 16:00 | 75 min | J1 - J3 Synthesis | Parallel Breakouts | Deep Dive: Data Transformation, Schemas & Regional Interoperability Accords |  | Tech Deep Dive: StructureMap Execution, Validator Runs & Discrepancy Repair | Executing ConceptMap & StructureMap pipelines, running CLI validators, debugging JSON payload validation errors across country schemas. | Policy Deep Dive: National Interoperability Governance & Data Exchange Legal Agreements | Cross-border health data exchange treaties, trust frameworks, patient privacy guarantees under PDPA/GDPR equivalents. | Validated J1-J3 ConceptMaps & Bilateral Data Exchange Framework Draft | Scheduled
16:00 - 17:00 | 60 min | Day 1 Synthesis | Plenary Session | Joint Synthesis Plenary: Cross-Workstream Debrief & Evidence Review for Journeys J1-J3 |  | Joint Review: Tech Lead Demos of Validated Data Pipelines & Provenance Logs | How do technical mappings resolve policy bottlenecks, and what policy constraints dictate API specifications? | Joint Review: Presentation of Draft Governance Accords & Multi-Country Consensus Points | What legal obstacles remain unresolved for cross-border vaccine verification prior to Day 2 travel flows? | Day 1 Consensus Summary & Day 2 Readiness Sign-off | Scheduled

## Day 2 Agenda
THAILAND WORKSHOP • DAY 2 AGENDA: OUTBOUND TRAVEL (J4), PROJECTATHON PRACTICUM (J5) & JOINT DEMO
Schedule: Day 2 (09:00 - 17:00) • Venue: Bangkok Grand Ballroom, Sandbox Stations 1-3 & Policy Chamber • Focus: Verifiable Health Links, Projectathon Testing & Multi-Country Interoperability
Time Block | Duration | Journey Ref | Session Format | Plenary Anchor & Joint Scope | Technical Breakout (Room A / Testing) | Technical Guiding Questions | Policy & Governance Breakout (Room B) | Policy Guiding Questions | Session Output / Deliverable | Execution Status
09:00 - 09:30 | 30 min | Framing | Plenary Session | Day 2 Opening & Outbound Family Travel Framing (J4.0 / J4.1) | All Participants in Grand Ballroom | How does mobile VHL architecture decouple secure credential storage from cross-border point-of-care verification? | All Participants in Grand Ballroom | What legal frameworks govern shared family mobile credentials and dependent data sovereignty? | Day 2 Interoperability Goals & Testing Ground Rules | Scheduled
09:30 - 10:45 | 75 min | Journey J4 | Plenary & Breakouts | J4 Walkthrough: Outbound Family Travel & "One Family, One Phone" VHL (15m Plenary intro) | Tech Breakout (60m): Multi-Profile Mobile VHL, OHS Player Config & Mock VHL Issuer Endpoint | Multi-profile mobile management in OHS Player; VHL issuer mock service; AuditEvent logging at Info Gateway; passcode decryption and verification via shared library. | Policy Breakout (60m): Minor/Dependent Consent, Data Retention, VHL Expiration & Legal Audits | National portal access & identity verification; consent to share minor/dependent records; link lifetime & data retention; legal basis for cross-border access; audit trail governance. | VHL Multi-Record Architecture & Cross-Border Consent Governance Charter | Scheduled
10:45 - 11:00 | 15 min | Intermission | Health Break | Morning Refreshments & Projectathon Sandbox Station Transition | Grand Foyer Refreshments & Sandbox Station Staging | N/A - Testing Environment Verification | Grand Foyer Refreshments & Policy Roundtable Prep | N/A - Discussion Group Preparation | Informal Networking & System Staging | Scheduled
11:00 - 12:30 | 90 min | Journey J5 | Testing & Policy Tracks | Projectathon Practicum - Exchange Testing Part 1 (Stations 1 & 2) | Tech Track: Station 1 (Source Schema to FHIR Transformation) & Station 2 (Read/Write REST API Transactions) | Executing FHIR mapping pipelines, testing REST API endpoints between country nodes (TH, ID, MY, LA, KH), verifying HTTP status codes and schema conformance. | Policy Track: Country Implementation Readiness Assessment & Institutional Governance Checklists | Evaluating national readiness checklists, legal mandates for digital health interoperability, institutional governance for regional trust lists. | Projectathon Exchange Test Log (Stations 1 & 2) & Country Readiness Scorecards | Scheduled
12:30 - 13:30 | 60 min | Intermission | Meal Break | Networking Luncheon & Sandbox Debugging Pods | Dining Pavilion & Country Debugging Pods | N/A - Peer Networking & Ad-hoc Debugging | Dining Pavilion & Bilateral Discussion Pods | N/A - Bilateral Policy Dialogues | Country Bilateral Exchanges | Scheduled
13:30 - 15:00 | 90 min | Journey J5 | Testing & Policy Tracks | Projectathon Practicum - Advanced Interoperability & Extensions (Station 3) | Tech Track: Station 3 (Interoperability Checks & WHO-ITB / ICVP Test Suite Execution) | Running WHO-ITB (Gazelle) test suites, executing International Certificate of Vaccination or Prophylaxis (ICVP) test assertions, end-to-end payload signing. | Policy Track: Sustained Regional Capacity, Trust Frameworks & ASEAN Policy Roadmap | Formulating 24-month regional interoperability roadmap, establishing regional digital trust council, harmonizing terminology governance across ASEAN. | Validated WHO-ITB Test Assertions & ASEAN Regional Policy Roadmap Draft | Scheduled
15:00 - 15:15 | 15 min | Intermission | Health Break | Afternoon Refreshments & Demonstration Assembly Staging | Grand Foyer Refreshments | N/A - Demo Rehearsal Setup | Grand Foyer Refreshments | N/A - Policy Debrief Prep | Informal Networking | Scheduled
15:15 - 16:00 | 45 min | Assembly | Plenary Session | Demonstration Assembly: End-to-End System Integration Rehearsal (J1 through J5) | Tech Leads & Developers: Live Dry-Run of Cross-Border Data Flow (J1 Birth to J4 Travel to J5 Verification) | Verifying cross-border transaction latency, QR payload parsing on physical devices, and fallback offline synchronization. | Policy Leads & Directors: Review of Harmonized Policy Statements & Interoperability Declaration | Aligning ministerial briefing points, review of cross-border data privacy consensus language. | Verified End-to-End Live Rehearsal & Polished Plenary Slide Deck | Scheduled
16:00 - 17:00 | 60 min | Culmination | Plenary Session | Joint Demonstration Plenary: Connected E2E Journey Showcase & Policy Recommendations | All Delegations: Live Demonstration of Connected Health Journeys J1 - J5 across Member States | Live presentation of end-to-end interoperability proof-of-concept connecting national registries across ASEAN. | Delegation Leads & WHO Representatives: High-Level Policy Recommendations & Closing Communiqué | Presentation of regional governance recommendations, ministerial adoption roadmap, and signed workshop declaration. | Workshop Final Communiqué & Regional Interoperability Adoption Roadmap | Scheduled

## Deliverables & Governance
THAILAND WORKSHOP • DELIVERABLES, TECHNICAL ARTIFACTS & POLICY GOVERNANCE REGISTER
Integrated Register: Technical Specifications, FHIR Profiles, Policy Accords, and Projectathon Test Acceptance Criteria for J1 through J5
Deliverable ID | Journey Ref | Workstream Track | Deliverable Title & Technical Scope | Standard / Legal Instrument | Acceptance Criteria & Artifact Proof | Lead Country / Workstream | Governance Status | Target Milestone
DEL-01 | Journey J1 | Technical Track | FHIR Patient & Immunization Core Profiles for Newborns | HL7 FHIR R4, WHO DDCC Core Profiles | Profiles validate newborn demographics, birth dose antigens (Hep B, BCG, OPV), and maternal linkage extensions | Technical Track (Thailand / WHO) | Under Review | Day 1 Session 2 (10:30)
DEL-02 | Journey J1 | Technical Track | Digital Vaccine Certificate (DVC) QR Payload Specification | SMART Health Cards / W3C Verifiable Credentials | Binary and JSON schema definition supporting signed 2D barcode printing with minimal edge footprint | Technical Track (WHO / Malaysia) | In Development | Day 1 Session 2 (10:30)
DEL-03 | Journey J1 | Policy Track | Cross-Border Routine DVC Recognition Guideline | Regional Health Legal Framework | Guideline detailing sovereign recognition criteria of routine foreign immunization records without bilateral treaties | Policy Track (Thailand MOPH) | Under Review | Day 1 Session 2 (10:30)
DEL-04 | Journey J1 | Policy Track | CRVS & Foreign Birth Notification Policy Brief | Civil Registration & Vital Statistics (CRVS) Accords | Policy model for cross-border consular and health facility notification of births to domestic registries | Policy Track (Lao PDR / Cambodia) | Draft Proposed | Day 1 Session 2 (10:30)
DEL-05 | Journey J2 | Technical Track | Offline-First Android CHW App Configuration (OHS Player) | OHS Player, Android Jetpack, FHIR SQLite | Configured client app capable of scanning paper DVC QR offline, parsing payload, and storing local records | Technical Track (Lao PDR / WHO) | In Development | Day 1 Session 4 (12:00)
DEL-06 | Journey J2 | Technical Track | FHIR ServiceRequest Referral Workflow Definition | HL7 FHIR R4 ServiceRequest, Task | Standardized referral payload generated by CHW for local clinic triage with embedded immunization metadata | Technical Track (Cambodia / Indonesia) | In Development | Day 1 Session 4 (12:00)
DEL-07 | Journey J2 | Policy Track | CHW Scope of Practice & Foreign Record Protocol | National Primary Healthcare Directives | Standard Operating Procedure defining legal limits for CHWs logging unverified foreign health data | Policy Track (Cambodia / Lao PDR) | Draft Proposed | Day 1 Session 4 (12:00)
DEL-08 | Journey J3 | Technical Track | Kotlin Multiplatform Cryptographic Verification Library | Kotlin Multiplatform, ECDSA P-256 / RSA | Cross-platform library (Android, iOS, Web) validating DVC digital signatures against regional trust list | Technical Track (Thailand NDHP / MY) | In Development | Day 1 Session 6 (14:30)
DEL-09 | Journey J3 | Technical Track | FHIR PlanDefinition Schedule Evaluation Ruleset | HL7 FHIR R4 PlanDefinition, FHIRPath | Rule engine evaluating domestic national immunization schedules against ingested foreign vaccine history | Technical Track (Malaysia MOH) | In Development | Day 1 Session 6 (14:30)
DEL-10 | Journey J3 | Policy Track | Regional Trust-List Key Governance Protocol | PKI Governance, Trust-List Framework | Key rotation, revocation, and mutual root authority recognition guidelines among ASEAN member states | Policy Track (Regional Steering) | Under Review | Day 1 Session 6 (14:30)
DEL-11 | J1 - J3 Synthesis | Technical Track | ConceptMap & StructureMap Regional Data Transformation Suite | HL7 FHIR Mapping Language (FML), ConceptMap | Automated transformation mappings converting source EHR schemas and local vaccine codes to FHIR DDCC | Technical Track (Joint Country Techs) | Draft Proposed | Day 1 Session 8 (16:00)
DEL-12 | Journey J4 | Technical Track | Verifiable Health Link (VHL) Mock Issuer & Decoder Endpoint | SMART Health Links / VHL Core Spec | Mock server emitting passcode-encrypted VHL QR codes and decoder validating multi-profile manifests | Technical Track (Indonesia SatuSehat) | Draft Proposed | Day 2 Session 2 (10:45)
DEL-13 | Journey J4 | Policy Track | Minor Dependent Data Sharing & VHL Expiration Framework | ASEAN Framework on Personal Data Protection | Privacy safeguards, legal parental consent delegation, and strict link expiration/retention constraints | Policy Track (Indonesia Kemenkes) | Draft Proposed | Day 2 Session 2 (10:45)
DEL-14 | Journey J5 | Technical Track | Projectathon Test Assertion Matrix & REST API Verification Log | WHO-ITB (Gazelle), Postman Collections | Executed test logs demonstrating successful FHIR validation and REST API exchanges across all 5 nations | Technical Track (All Member States) | Draft Proposed | Day 2 Session 6 (15:00)
DEL-15 | Journey J5 | Policy Track | ASEAN Digital Health Interoperability Declaration & Policy Roadmap | Regional Ministerial Declaration | Multilateral communique setting 24-month roadmap for cross-border digital health trust list operations | Policy Track (All Delegation Leads) | Draft Proposed | Day 2 Session 9 (17:00)
DEL-16 | J1 - J5 Synthesis | Technical Track | End-to-End Live Demonstration System Script & Architecture Package | HL7 FHIR, DDCC, IPS, VHL, OHS Player | Unified script and recorded evidence trace of connected journey flow from J1 birth to J5 verification | Joint Demonstration Team | Draft Proposed | Day 2 Session 9 (17:00)